## Slide 1
Monitoring & EVALUATION
Training
experiential

## Slide 2
Monitoring & EVALUATION
MODULE 5

## Slide 3
AGENDA
I - Data collection (continued) / focus on questionnaires
II- Data control
III- Analysis and use
IV- Information path
Notes: Check session 3 - dashboard presentation - to be updated

## Slide 4
PEDAGOGICAL OBJECTIVES - Session 5
At the end of this module, participants should be able to :
Tips for preparing a quality questionnaire
M&E implementation - data collection / dashboard use
Use table data for analysis, dialogue and decision-making
Use dashboard data for reporting and analysis.
Identify and implement the information path - the dashboard.
Notes: Exchange with participants to check ownership of dashboard objectives - 5 minutes

## Slide 5
QUESTION/ANSWER?
Experience feedback
How did you fill in the dashboard?
Have you encountered any particular difficulties?
Notes: Open up time for questions and answers on the individual work carried out: preparation of the dashboard - depending on the questions/difficulties - use the support from session 4 or use demonstrations on the dashboard and the case study.

## Slide 6
I - data collection (continued)

## Slide 7
DATA CYCLE
source CartONG
Notes: Situate the stage in the data cycle

## Slide 8
DESIGNING TOOLS
?
Reminder of module 4
What methods and tools can you use to collect data?
Contact: @secours-catholique.org @secours-catholique.org
Notes: Exchange with participants to check ownership of information concerning data collection in module 3 - 5 minutes

## Slide 9
DESIGNING TOOLS - FOCUS ON THE QUESTIONNAIRE
Checklist and tips for designing a form
Checklist | Explanations
Formulate understandable questions, with as little technical jargon as possible. Example: DE can have several meanings: Droit de l'enfant vs Diplôme d'Etat | Avoiding misconceptions and facilitating the appropriation of the form by teams and new interviewers by making the survey self-explanatory In multilingual contexts, this will also facilitate translation. Don't hesitate to add clues to explain the necessary definitions, or to replace text values with images where this can be useful. During training, use concrete examples, role-playing or answer standardization tests to ensure that everyone has the same understanding of the strategic questions.
Do not attempt to merge questions to reduce the total number of questions. | This complicates the answer and its analysis. So avoid double questions Example: Are there any disabled and/or elderly people, and if so, how many? Replace with: number of disabled people / number of elderly people

## Slide 10
Checklist and tips for designing a form
Checklist | Explanations
Avoid free-text answers | This complicates the analysis, as it requires individual reading of each answer. If necessary, specify a short answer or key words. Prefer standardized answers, with a choice of answers (response options already formulated) that will make analysis easier.
Limit multiple-choice answers | They may appear to be an option, but their analysis requires a great deal of manipulation (filtering, cross-referencing of data and information), which can make analysis more complex and require technical skills.
Keep the question neutral: don't try to influence the respondent. | This will obviously bias the results by encouraging an answer that may not be true.
DESIGNING TOOLS - FOCUS ON THE QUESTIONNAIRE

## Slide 11
Checklist | Explanations
Make sure your survey flows logically from one question to the next, and from one group of questions to the next. | This makes it easier for the respondent to read and understand. If they get lost in the questions, they may abandon the form.
Contextualize issues that may directly affect the people concerned. Example: "Are you satisfied with services provided to your family ? “ | If you don't explain that the answer to this question will have no impact on any additional help you may be able to provide, you run the risk of obtaining a highly underestimated result...
Checklist and tips for designing a form
DESIGNING TOOLS - FOCUS ON THE QUESTIONNAIRE

## Slide 12
Checklist | Explanations
Consider the reasons for making questions compulsory | Certain questions can be made compulsory, to improve the quality of the analysis. However, the following questions should be considered: for technical reasons (especially on mobile devices) where certain data (GPS, for example) may not work, thus blocking the rest of the form; some questionnaires depend on several people. If they are not available at the time of the survey, it will not be possible to complete the form; if you're not sure about the suggested answers, or even the relevance of the question, it's best to leave it open-ended. Failure to answer a question is in itself data that you can analyze: the question is not well formulated, the subject of the question is not perceived by the people concerned.... people might be tempted to answer randomly, without conviction, and move on to the next question, which would skew the quality of the data.
Checklist and tips for designing a form
DESIGNING TOOLS - FOCUS ON THE QUESTIONNAIRE

## Slide 13
Comparison between mobile data collection (MDC) and PAPER BASE collection
Notes: Exchange with participants to check ownership of information concerning data collection in module 3 - 5 minutes

## Slide 14
QUESTIONNAIRE SUPPORT
Examples of digital media for mobile data collection
Koboo tool box: free for NGOs; easy, intuitive form design; question tree options. However, direct analysis on the platform is very limited (Koboo tool box is not an analysis tool). This requires data to be extracted into Excel for analysis; possibility of multi-language forms.
Google form: free; easy, intuitive form design; question tree structure remains linear (more difficult to condition a question to a specific answer / only to the previous answer); relatively complete answer analysis and excel extraction facility to complete the analysis if required; limited data protection.
Survey CTO: fee-based service; excel spreadsheet export is required for full data visualization; form design is possible on the platform; options for question tree structure; platform is in English.
To find out more: https://alnap.org/help-library/resources/benchmarking-de-solutions-de-collecte-de-donnees-sur-mobile-2021/
Notes: Exchange with participants to check ownership of information concerning data collection in module 3 - 5 minutes

## Slide 15
SURVEY - BEST PRACTICES
Analysis plan/ Dashboard
What is the desired level of quality
Is data collection necessary?
What data collection methods are most appropriate (consider the safety context for staff and beneficiaries)?
Sampling
Data collection tool
Technical tips and tricks (metadata, constraints, etc.)
Language
Language
Questionnaire length
Consent
Technical validation of the form / Technical test (form of results...)
Consider testing understanding of key words and concepts and survey feasibility
Standardization test
Pilot site
Continuous quality control of survey submissions
Frequent debriefing with interviewers
Language control during surveys
Survey feedback
Clean archiving
Form availability for other surveys
Feedback to respondents
Notes: Exchange with participants to check ownership of information concerning data collection in module 3 - 5 minutes

## Slide 16
QUESTION/ANSWER?
DESIGNING A QUESTIONNAIRE
Notes: Exchange with participants on the questionnaire design session

## Slide 17
II - DATA CONTROL

## Slide 18
DATA CYCLE
source CartONG
Notes: Situate the stage in the data cycle

## Slide 19
DATA QUALITY: What to think about?
-Validity - Question(s) asked
-Reliability - Collection method(s)
-Accuracy - Sampling strategy
-Integrity - Data processing and management processes
-Temporality - Calendar + PlanningAccuracy
Validity
Reliability
Accuracy
Integrity
Temporality
Notes: Validity - Data is valid when it accurately represents the variable/concept you intend to measure.
Reliability - Data is reliable when the collection methods used are stable and consistent. Reliable data are collected using tools such as questionnaires that can be implemented in the same way over and over again.
Accuracy - Data is accurate when there is little variation in the data. (Think of a "bull's eye"). Precision is very closely linked to sampling strategy.
Integrity - Data has integrity when it is accurate (complete and clean).
Timing - Data must be available when you need to use and share it. Data is of no use to you if it arrives too late to inform decision-making. This factor plays an important role in your data collection planning.

## Slide 20
In a monitoring-evaluation system, it is essential to check, control, clean and validate the data, whether in your database, your dashboard or the results of your questionnaires.
DATA CONTROL
Data entry errors can happen to anyone. Reviewing your data will enable you to detect errors. In Excel, signals can indicate these errors and enable you to rectify (clean up) the data.
In a large database, select a representative number of rows and check the consistency of the answers/data entered.
Identify common errors and ask questions :
the wording of your question
the interviewer, who in the event of a repeated error may not have entered the question.

## Slide 21
In a monitoring-evaluation system, it is essential to check, control, clean and validate the data, whether in your database, your dashboard or the results of your questionnaires.
DATA CONTROL
Provide your teams with regular feedback on data quality, so as to improve the data collected and entered in a pedagogical way.
Who in your team has been identified as carrying out this data control and cleansing, and when?
Data sharing and collective analysis time also help to check consistency, possible biases and data quality (difficulties encountered, etc.).

## Slide 22
III - PROTECTION
MODULE 5

## Slide 23
DATA PROTECTION - EXCHANGE TIME
?
What does the notion of data protection mean to you?
Have you already implemented data and respondent protection rules? If so, which ones?
Contact: @secours-catholique.org @secours-catholique.org
Notes: Open an exchange and discussion on data protection and participants' knowledge and experience

## Slide 24
ETHICAL CONSIDERATION OF DATA
-Informed consent
-Do no harm
-Confidentiality / Anonymity / Privacy
-Respect for the individual (respect for their time, experience, feelings - link with acceptance)
-Share results (provide "closing the loop" feedback)
-Physical protection (limit access, no unintentional sharing)
- Limit risks (collect only what will be used)
Notes: Validity - Data is valid when it accurately represents the variable/concept you intend to measure.
Reliability - Data is reliable when the collection methods used are stable and consistent. Reliable data are collected using tools such as questionnaires that can be implemented in the same way over and over again.
Accuracy - Data is accurate when there is little variation in the data. (Think of a "bull's eye"). Precision is very closely linked to sampling strategy.
Integrity - Data has integrity when it is accurate (complete and clean).
Timing - Data must be available when you need to use and share it. Data is of no use to you if it arrives too late to inform decision-making. This factor plays an important role in your data collection planning.

## Slide 25
DATA PROTECTION
Do you hold sensitive data?
Are they anonymized?
Where they are stored (paper or digital)
If you use a platform/cloud, is it protected?
How long do we need to keep and store this data? Identify a time limit for data storage.
Data protection must also be considered in terms of storage, accessibility and protection.
We need to ask ourselves, in light of the do no harm principle, but also national and international regulations (Europe: RGPD)

## Slide 26
III - ANALYSIS AND USE

## Slide 27
MONITORING & ASSESSMENT
TRAME TdR EVALUATION
REPORT FRAMES
DATA COLLECTION
DATA CONTROL, VERIFICATION AND CLEANING
DATA COMPILATION / DASHBOARD UPDATE
PERIODIC FOLLOW-UP MEETING
PROJECT DATABASE
START-UP
RACI
M&E PLAN
FINALIZING THE M&E PLAN
OPERATING PLAN OUTLINE
TRAME
M&E PLAN
DATA ANALYSIS
USE OF ANALYZED DATA FOR PROJECT MANAGEMENT
STEERING (MONITORING PROGRESS OF ACTIVITIES, ACHIEVEMENT OF INDICATORS, TARGETS, ETC.)
DECISION-MAKING (READJUSTMENT, UPDATING, ALLOCATION OF RESOURCES, ETC.)
BUDGETED OPERATIONAL PROJECT PLANNING MEETING AND PRESENTATION OF THE M&E
BOARD LAYOUT
DEFINITION OF ROLES AND RESPONSIBILITIES IN S&E (RACI)
DEFINITION OF COLLECTION TOOLS AND VERIFICATION SOURCES (SOV)
DASHBOARD SETTINGS
M&E CAPACITY-BUILDING PLAN (INTERNAL TEAM AND PARTNERS)
LAUNCH OF BASELINE STUDY
MANAGEMENT
QUARTERLY PROGRESS REPORT AND ANNUAL REPORT (Q4)
EXTERNAL REPORTS (DONORS, NATIONAL AUTHORITIES, CONSULTATION FRAMEWORK, ETC.)
INTERIM EVALUATION (PROJECT LASTING AT LEAST 3 YEARS)
INFORMATION SHARING, PARTICIPATORY APPROACH WITH STAKEHOLDERS
ADVOCACY AND INFLUENCE, EXTERNAL COMMUNICATION
ANNUAL PARTICIPATORY BALANCE SHEET
USE OF DATA FOR REPORTING
INFORMATION SHARING AND STAKEHOLDER FEEDBACK
BOARD LAYOUT
BOARD LAYOUT
THE IMPLEMENTATION PHASE
Notes: Situate the training stage in relation to the SE diagram

## Slide 28
DATA CYCLE
source CartONG
Notes: Situate the stage in the data cycle

## Slide 29
Data analysis is the application of techniques applied to data to reveal useful information and support decision-making.
-After data collection, each individual data item can be assembled into a "dataset" and, using data analysis techniques, provide useful information.
The information uncovered by data analysis can then be used to facilitate decision-making.
Contact: @secours-catholique.org @secours-catholique.org
DATA ANALYSIS

## Slide 30
Tab 2. Summary and analysis allows you to identify and visualize certain cross-referenced data.
Further analysis may be required.
Data without analysis can mean anything and everything, so it's important to put them into dialogue. It's a question of putting certain information into perspective, cross-referencing it with qualitative information and arguing it to make it relevant and coherent.
The dialogue must be based on a participatory approach involving the various stakeholders.
Contact: @secours-catholique.org @secours-catholique.org
DATA ANALYSIS - How do I do it?

## Slide 31
Follow-up of beneficiaries/people reached
A mis parcours de votre projet, voici les données concernant le profil genre des enfants touchées par le projet. What do you observe? How do you analyze and interpret this information? What kind of decisions need to be made for the project's future?
DATA ANALYSIS - Example
Notes: Ask participants what they see, how they analyze this information (many boys than girls), how to interpret it, argue it, what kind of decisions will have to be made?

## Slide 32
On tab 2 of the case study dashboard, analyze the various items of information.
Fill the "narrative indications" boxes with information, possible explanations, questions and possible decisions.
Propose a project status report based on the information reviewed and analyzed.
You may also identify issues related to the dashboard format: for example, what information would have been useful to include or visualize.
Present your findings in plenary (5 minutes per group)
EXERCISE - CASE STUDIES
You have 15 minutes.
Two working groups
Notes: A case study is available, and it is possible to form two groups. At the end of the group discussions, a debriefing session should be planned—each group will be required to deliver an oral presentation summarizing their case study project.Filling out the boxes is simply a support tool—by definition, it is fictional, so participants should project themselves into possible explanations or analyses. For this reason, they may, for example, formulate questions or define what should be discussed with teams or stakeholders in order to gather more information. The case study does not reflect all the information of a real project—it is therefore not about checking whether the information is accurate or consistent, but rather using it as a training tool. The budget tab is not included in the case study.

## Slide 33
?
How do you think you can use the information you've gathered in the ES (illustrated in the dashboard)?
As a project manager, how can this information help you manage your project?
What are you going to do with this information?
Contact: @secours-catholique.org @secours-catholique.org
USES - EXCHANGE TIME
Notes: Following the case study dashboard data analysis exercise, open a discussion with participants on the possible uses of this information: what decisions can be made? what use can it be for the project manager, but also in terms of communication with stakeholders....

## Slide 34
USES
Steering (monitoring progress of activities, achievement of indicators, targets, etc.)
Advocacy and influence, external communication
Decision-making (readjustment, updating, allocation of resources, etc.)
Annual participatory review
Information sharing, participatory approach with stakeholders
Use of analyzed data for project management
Use action plan management and progress monitoring information. What decisions should be taken for activities that are significantly behind schedule?
Make decisions regarding budget consumption
Check the relevance of indicators
Redirect activities if necessary
Communicate information to partners and share information (explain delays, progress, results, etc.).
Ensure accountability to partners and transparency
Contribute to horizontal and collective management
Use data to inform, influence and advocate: your data and statistics on the people affected/concerned (school enrolment rates, results achieved...).
Notes: Summarize the previous discussions by presenting the various uses - also recall that the data are used to facilitate the production of reports

## Slide 35
III - INFORMATION PATH

## Slide 36
The point of a monitoring-evaluation system and data management is to circulate information.
It is therefore essential to clearly define the data and information flow in the M&E plan (document word).
Contact: @secours-catholique.org @secours-catholique.org
Who takes part in the analysis?
DATA AND INFORMATION PATH
Who holds the information?
Who does he give it to?
Who records the data (DB/Dashboard)?
Who takes part in the analysis?
Who do we send information to?
Who do we give information back to?
This step is often overlooked, yet it is essential to the principle of accountability.

## Slide 37
Monthly - no later than the XXth of each month
When?
Sharing the dashboard - Country Direction
What?
Who?
Dashboard update: tab 3 (action plan), tab 4 (indicator tracking)
Project manager (in collaboration with MEAL manager?)
Monthly - no later than the XXth of each month
Dialogue and data analysis - monthly project follow-up meeting.
Complete the "analysis" boxes in Tab 2 (balance sheet and analysis)
Project team members, support teams and operational partners involved, regional team (optional participants /Project
Quarterly - no later than the XXth of each quarter
Dialogue/reconciliation tab 5, budget monitoring, and accounting data, complete comments column
The project manager and administrative manager
from : Project managers
to : Country Director
cc: Administrative manager, logistics manager? partners?xxxx
Quarterly - no later than the XXth of each quarter
Monthly - no later than the XXth of each month
Sharing the dashboard (in addition to the quarterly report) with Director of Programs and Technical Resources
from : Country Director
to : Regional Programs Coordinator
cc: Regional Finance and Support Services Coordinator
Quarterly - no later than the XXth of each quarter
Sharing feedback, comments, questions, analysis, needs, from international management to the project team
from : Regional Programs Coordinator
to : Project Manager
cc: Country Director
DATA AND INFORMATION PATH
Example - Dashboard
Notes: Show the example of the dashboard path

## Slide 38
When?
What?
Who?
Quarterly - no later than XX
Complete quarterly progress report (cumulative report T1/T2/T3/T4)
The project manager
from : Project managers
to : CD
cc :
Quarterly - no later than XX
Review of quarterly report by regional programs coordinator
The regional programs coordinator
Quarterly - no later than XX
Sharing feedback, comments, questions, analysis, needs, from international management to the project team
The regional programs coordinator
from : Regional Programs Coordinator
to : Project Manager
cc: Country Director + XXXXXX
Quarterly - no later than XX
Review and compilation of quarterly progress reports
CD
from : CD
to : Regional Programs Coordinator and Director Programs and Technical Resources
cc :
DATA AND INFORMATION PATH
Example - Dashboard

## Slide 39
In the M&E plan (word document), section 4.2 information management; diagram the data and information path of your own project, specifying the stakeholders involved.
EXERCISE
You have 10 mins.
INDIVIDUALLY
Notes: Optional - depending on the time available - Suggest that one or two participants present their own diagrams.

## Slide 40
KEY MESSAGES
TO REMEMBER
Data collection :
Design your questionnaire to suit your audience. Limit questions to essential information.
An important data quality control and cleaning step to ensure the reliability of the analysis.
The guiding principle is to do no harm when collecting and using data
Data collection :
All data must be analyzed to become relevant, usable and shareable information.
A collective and participative analysis
Using data to enhance project management efficiency and accountability.
Notes: Data collection and data analysis

## Slide 41
Transition and closing phase :
M&E process and milestones for project closure
How to prepare a final evaluation
End of training :
Reviews
Next module

## Slide 42
INSTRUCTIONS INDIVIDUAL WORK

## Slide 43
Continue work on setting dashboard parameters, in particular tab 2 - balance sheet and analysis
Initiate data entry in tab 3 (action plan) and tab 4.2 (indicator tracking).
View the first possible analyses
INDIVIDUAL WORK
Notes: Note the good practices mentioned by participants

## Slide 44
END OF SESSION 5
THANK YOU!