## 0 - Guide
USER GUIDE
MONITORING & EVALUATION DASHBOARD
This dashboard is an experimental tool. The pilot phase of the M&E deployment should enable us to verify its usefulness and functionality. The aim is to test it, so that it can be optimized and improved. What is not useful will be removed, and what is missing will be added. Experimentation is therefore part of a learning process for the tool itself. It is not, therefore, a version that claims to be definitive and set in stone.
Tabs | Objectives | Update (recommended) | PARTICIPANTS FEEDBACK
Tab 0 - Guide | Explanatory notes on using the project dashboard | revision/updating of the SE guide - produced by the International Division
Tab 1 - Project Information | This tab provides an overview of the main features of the project, including the actors/partners involved in the project, as well as the direct and indirect stakeholders/beneficiaries. It recalls the project's logical framework. | In the event of a significant change to the project (Cost extension, No Cost, delay, major reorientation of activity)
Tab 2 - Review & Analysis | This tab provides a visual summary (diagrams) of the project’s main indicators as well as project management and monitoring information. It is made up of two sections: On the left: a section dedicated to project data in terms of direct beneficiaries, indirect beneficiaries, confirmed persons, and key indicators. The beneficiary chart is automated but can be adjusted or modified if needed. However, regarding the key indicators—particularly those that can be aggregated at the international level—pre-configuration is not possible because it depends on the project’s choices. Therefore, configuration must be carried out at the beginning of the project. On the right: a section dedicated to project management data, corresponding more to metadata. These allow the tracking of project implementation. All formulas are pre-configured, and the data are linked to different tabs (Tab 3 – Action Plan; Tab 4.2 – Indicators Monitoring; Tab 5 – Budget Implementation Monitoring). They update automatically depending on changes made in the “3_Action Plan,” “4.2_Indicators Monitoring,” and “5_Budget Implementation Monitoring” tabs. Next to each indicator, a space (white box) is dedicated to narrative analysis. This box must be filled in manually after collective analysis discussions with the project team. These elements are essential to explain, provide context, and justify certain data, considering that the dashboard will be shared with regional coordination. Finally, check whether it is necessary to keep an annual record/history. Otherwise, the tab will continue to update throughout the project without retaining past data—so it may be necessary to make regular copies. | Quarterly
Tab 3 - Action Plan | This tab must be filled in and aligned with the project action plan. It will identify when activities are due to be implemented during the life of the project, and will allow you to track the completion of activities as they are carried out. It should be reviewed and updated in parallel with monthly internal reporting. For each activity line, there is a dialogue area (column AM; AN; AO). Project teams can provide explanatory information on the status of certain activities, and identify the decisions taken in the next column. Regional coordination can provide feedback, recommendations and questions in the last column.) This tab requires settings at the start of the project: Column C: note each activity and sub-activity of your action plan on each line. You can detail your activities as much as you like. Column D: activity target, if relevant - some activities may not have a target, in which case leave it blank. Column E: unit - specify the unit of the activity: sessions; people.... Columns F and G are autimatic and already parameterized. Column H: this column links to the budget line of the activity line and refers to data in tab 5. It must be set at the start of the project. Columns K and L: the planned line must be filled in with the forecast dates in DD/MM/YYYY format; the completed line is filled in progressively in the same format. Column I: Status is a drop-down list. It must be filled in following a monthly team dialogue on the status of the activity. Time settings: the number of months in the project must be adjusted (on the screen it is 24 months, but you can add or delete columns according to the duration of your project). The dates in rows 3 and 4 of the month columns must be updated to reflect the dates of your project. You can add quantity concepts in each cell, which will enable you to calculate the achievement of the target in terms of activity. | Monthly
Tab 4.1 - M&E Plan | This tab contains the indicators from the M&E plan (narrative support accompanying the dashboard). It is used to define the project's indicators, their definition, and the collection tools....It is filled in at the start of the project. This is an informative tab, and will not be modified except in the event of a major change to the project that would impact the M&E indicators. | In the event of significant changes to the project and project indicators
Tab 4.2 - Indicators Monitoring | This tab reproduces the indicators from the M&E plan, tab 4.1. Columns B & C are automatic. It facilitates monthly data recording. At the same time, you don't have to fill in each indicator every month. It includes automatic formulas for tracking the quantitative progress of each indicator. The pre-existing parameters are basic (sums) and must be updated at the start of the project according to the calculation mode for each indicator. The calculation mode is set in column G at the start of the project. The figures entered can be linked to Tab 2 - Balance sheet and analysis.
Tab 4.3 Beneficiary Monitoring | This tab allows you to track beneficiaries by profile, using the harmonized ACTEI GPMF format. There is a table of direct beneficiaries and a table of indirect beneficiaries by quarter. At the bottom, a total table automatically calculates the totall of all quarters. In the basic framework, 4 quarters are parameterized. Additional tables can be added if required. In this case, the total table is revised to adjust the calculation formulas. This total table is linked to the 2-balance and analysis tab.
Tab 5 - Budget Implementation Monitoring | This tab contains the detailed budget for each project and the monthly forecast. It must be completed each month by the project manager (pre-filling in known information) in collaboration with the administrative manager (reconciliation) according to the expenses incurred. A monthly reconciliation is carried out to compare operational and accounting data. One section is dedicated to qualitative note-taking, column AY and AZ. It consists of 3 sections: 1 section for the initial budget forecast, corresponding to the project budget at the time of conception/ donor budget. Budget line codes must be supplied by the administrative manager. This budget is filled in at the start of the project. 2nd section dedicated to the actual budget per month. Automatic calculations are set up to track line realizations. This section is updated every month. 3rd section dedicated to the new forecast, i.e. the remaining months. Automatic calculations are set up to monitor line completion. Automatic calculations are set up to track line completion. This section is updated every month. Please note: this tab remains a project management and monitoring tool. It is intended to facilitate the operational reading of the project. It is in no way an accounting tool. Only the accounting tool (ERP5) is used for financial reporting. | Monthly

## 1 - PROJECT INFORMATION
UPDATE DATE
PROJECT INFORMATION | [12 empty] | PARTICIPANTS FEEDBACK
I- General information
Program/project title | Gender Equality through Vocational and Entrepreneurship Education (GEVEE)
ERP5 code | AFR008
Priority themes (is it possible to have more than one priority theme in a project? if not, just one box to answer the question) | LL&VT - Lifelong learning and socio-professional integration | [8 empty] | Economic empowerment and gender equality
Key themes (several key themes possible)
Cross-cutting themes ( several key themes possible) | Gender
General objective of the project | Promote gender equality and economic empowerment of marginalized women and girls in Laos and Vietnam
Intervention area(s) | Lao (Khammoun and Oudomxay) and Vietnam
Project target group(s) | Specify the people concerned, the project's target populations (list the main categories - as mentioned in the synoptic sheet)
Project dates & duration | Project start date |  | 2023-01-12 | Project end date |  | 2026-02-28 |  | Duration |  | 15 months
New phase of a previous project? | No |  | If yes, please specify previous projects (name, dates, lessor...)
II- Budget
Budget | Currency |  | Euros | Total |  | 500000 |  | Amount spent (at update date) |  | 200000
Lessor | Lessor's name |  |  | Amount of subsidy |  | Amount and currencies |  | Contract dates |  | DD/MM/YYYY |  | DD/MM/YYYY
- If co-financed - Lessor 1 | Lessor's name |  |  | Amount of subsidy |  | Amount and currencies |  | Contract dates |  | DD/MM/YYYY |  | DD/MM/YYYY
Add as many lines as necessary
III- ACTEI contact persons
Project contact | Name | First name | Position | e-mail | phone
| Sengthong Phothisane | Sengthong | Country Director | sengthong.phothisane@action-education.org
| Oulayphone Dethkongxay | Oulayphone | Program Quality and Development Manager (PQD) | oulayphone.dethkongxay@action-education.org
| Chindavanh Vongvilay | Chindavanh | Finance, Admin and HR Manager | chindavanh.vongvilay@action-education.org
| Viengsavanh Aloun | Viengsavanh | Program Officer | viengsavanh.aloun@action-education.org
| Vaiyakone Patoumphone | Vaiyakone | Program Officer | vaiyakone.patoumphone@action-education.org
IV- Partners
Consortium project? | No |  | If yes, specify who the lead is :
Project with operational partners? | Yes |  | If yes, please specify the partner information below.
Implementation partners | Nature/Profile of partner |  |  | Project role or category? |  | Signature of agreement |  | Comments
Gender Development Association (GDA) | Others |  |  | Operational (local NGO; CSO...) |  | Yes
National committee advancement for women and child committee (NCAWCC) | Others |  |  | Operational (local NGO; CSO...) |  | Yes
Actor 3
Actor 4
Add as many lines as necessary
TOTAL PARTNERS BY CATEGORY (automatic calculation) | Institutional | 1 | PTF | 1 | Operational | 1
V - Target populations / People concerned / Beneficiaries (GPMF classification)
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 832 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 6626 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
VI - LOGICAL FRAMEWORK OF THE PROJECT (as mentioned in the synoptic sheet)
Overall objectives
Specific objectives (add rows if necessary)
Main expected results (add rows if necessary)
Main activities (add rows if necessary)

## 2 - REVIEW AND ANALYSIS
REVIEW AND ANALYSIS
UPDATE DATE
PROJECT DATA |  |  |  | PROJECT MANAGEMENT / STEERING DATA
I- | MONITORING OF TARGET DIRECT BENEFICIARIES | MONITORING OF TARGET INDIRECT BENEFICIARIES | [date updated] Narrative indications / data analysis / explanations.... | I- | MONITORING THE IMPLEMENTATION OF ACTIVITIES
[date updated] Narrative indications / data analysis / explanations....
|  |  |  | Time-based activities | 0
|  |  |  | Late activities | 0
|  |  |  | Activities ahead of schedule | 0
|  |  |  | Completed activities | 0
Diagram linked to tab 4.3 - automatic, but profiles can be filtered by diagram data range |  | Diagram linked to tab 4.3 - automatic, but profiles can be filtered by diagram data range
Others forms of diagrams can also be set up |  | Others forms of diagrams can also be set up
II- | CUMULABLE INDICATORS ACTEI - to be configured for each project |  |  | II- | INDICATOR ACHIEVEMENT MONITORING
[date updated] Narrative indications / data analysis / explanations....
2.1 Indicator name |  |  |  | Indicators definitively achieved (100% or more) | 4
|  |  | "[date updated] Narrative indications / data analysis / explanations.... What was the subject of the satisfaction survey? - What does it mean for the project? | Indicators almost reached (75% and 100%) | 0
|  |  |  | Indicators partially achieved (50% and 75%) | 0
|  |  |  | Indicators only slightly achieved (25% and 50%) | 0
|  |  |  | Indicators not reached (0 and 25%) | 0
2.2Indicator wording
|  |  | "[date updated] | III- | BUDGET FOLLOW-UP
|  |  |  | To be completed manually according to the chapter headings in your project |  | [date updated] Narrative indications / data analysis / explanations....
|  |  |  | Budget chapter 1 :XXXXX | =Tab 5 - column Z Line corresponding to chapter total
|  |  |  | Budget section 2:XXXXX | =Tab 5 - column Z Line corresponding to chapter total
|  |  |  | Budget chapter 3: :XXXXX | =Tab 5 - column Z Line corresponding to chapter total
….
PARTICIPANTS FEEDBACK

## 3 - ACTION PLAN
CHRONOGRAM |  | manual filling | [7 empty] | Setup at the start of the project |  |  | duration to suit your project
UPDATE DATE |  | Activities | TARGET | Unit | Total Actual | % Technical achievement | Budget %. | STATUS | Planned/ Realized | Start date | End date |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | COMMENTS / QUALITATIVE INFORMATION ON THE SITUATION (to be completed by the project manager at the monthly follow-up meeting) | DECISION MAKING, MITIGATION MEASURES, SOLUTIONS PROPOSED (to be completed by the project manager during the monthly follow-up meeting) | REGIONAL MANAGEMENT FEEDBACK (to be completed by regional coordinator in response to comments, questions, suggestions, solutions...) | PARTICIPANTS FEEDBACK
[13 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
[13 empty] | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31
LAUNCH PHASE |  | team recruitement | 10 | pers | 5 | 50% |  |  | Planned | 2025-04-01 | 2025-05-31 | - | bar: 2025-04-30 to 2025-05-31
[9 empty] | Realized | 2026-06-01 | 2025-12-31 | - | 2025-06-30: 5
|  | training of teachers | 3 | sessions | 3 | 100% |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | - | bar: 2025-08-31; 2025-10-31; 2025-12-31
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
IMPLEMENTATION PHASE | 1. OS/ RSEULATS - timer/logic frame settings
|  |  | 12 |  | 3 | 25% |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | - | 2025-04-30: 3
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
2.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
3.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
1.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
2.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
TRANSITION PHASE & CLOSING | 1.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
2.
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
Note on H2: ====== ID#AAABicsSqCM (2025-04-24 09:01:05) Paramétrage au début du projet : = onglet 5 colonne Z / identification de la ligne correspondante -darnaudet valerie
Note on I2: ====== ID#AAABlHVwlTw darnaudet valerie (2025-06-03 15:42:23) Manual entry – after discussion with the team. The notions of delay or being ahead of schedule must be meaningful, as they should trigger an alert. The goal is not to highlight minor delays of a few days that have no real impact on the project timeline.

## 4.1 - M&E Plan
MONITORING AND EVALUATION PLAN - Presentation of indicators
Orange columns - taken from indicator database / blue columns - project-specific information | [18 empty] | PARTICIPANTS FEEDBACK
Description: Identification of the thematic priority in line with the ACTEI 2025-2029 strategy. | Description: Indicates the level of the results chain with which the indicator is associated. (Impact/effects/products/activities) | Specific formulation of the indicator | Description: Name or title of the indicator. It summarizes in a few words the objective or dimension being measured. Example: Enrolment rate for children aged 6 to 11. | Description: Provides a detailed and precise explanation of the indicator, clarifying its components, scope and purpose. Example: Percentage of pupils completing primary education with sufficient literacy and numeracy skills. | Description: indicates whether an indicator can be aggregated across the various ACTEI projects. This means that the data collected for this indicator can be added up over several time periods or between several projects to obtain a relevant overall total. | Description: Identification of the key action in line with the ACTEI 2025-2029 strategy. | Description: Specifies the nature of the data collected. Options: Numeric: A raw value (e.g. 500 schools renovated). Percentage: A proportion (e.g. 80% of teachers trained). Categorical: Classified data (e.g. low/medium/high). | Description: The unit of measurement used for the indicator. Example: people, schools, projects, communities | Description: Levels or categories according to which data can be broken down for finer analysis. Example: Gender, age range, geographic area | Description: Explains how the indicator value is obtained, detailing the calculation steps or formulas. Example: Number of children attending school divided by the total number of eligible children. | Project- and context-specific uses | Specify the people and/or team of partners who will collect the information | Specify from whom the information will be collected, who is the source of the information, who holds it? | How often or when should training be collected? | What tool, method or source of verification should be used to collect the information? | Is the tool ready yet? | Who is responsible for entering data into the dashboard? | Who will participate in the analysis of this data?
Thematic priority | Perimeter | Indicator label - project-specific | Indicator label (indicator bank formulation - if relevant) N.A if the indicator does not refer to any bank indicator and is specific to the project | Indicator definition | Cumulative ACTEI | Key action | Type of indicator | Observed unit | Disaggregations | Calculation methodology | For the project | Who collects? | Who holds the information (from whom is the data collected?) | When (collection frequency) | Which tools? | Tool status | Who enters the data into the dashboard? | Who analyzes?
LL&VT | Outcome/Effect | % of young women targeted by GEVEE will experience an increase in resources and improved attitudes towards working women |  | Resources Increased: Increased in income and wages Increase in access and use of services and benefits Increase in job opportunities, training/education, and career advancement Increase in ability to access and control financial and material resources Improved Attitudes: Positive attitudes, support and appreciation for women's roles and contributions at work Reduction in gender bias and discrimination against working women Commitment and policies to promote gender equality in the workplace Support and favorable conditions for working women, such as family care and career development | No |  | Percentage | People | Gender | Number of young women who have gained access to resources such as education, training, financial support, mentorship, or other opportunities that enhance their capabilities for employment. AND, those who have have a positive change in their attitudes towards working women, such as increased support, acceptance, or reduced gender-based biases agaist baseline value. |  | External consultant | Women in the target area | Baseline, midterm, and Endline | TBC | In Progress |  | External consultant | The template looks good, but it would be easier to fill in if there were examples of what is expected in each cell at least one or two indicators.
LL&VT | Outcome/Effect | By end of the project, % of GEVEE women will have increased access to financial, social or physical capital for personal advancement (adapted from ICRW4 ) |  | ICRW4 Resources are the building blocks women can draw on to succeed economically or to exercise power and agency. Resources can be at the individual or community level. They are more than financial or monetary in nature, and include: • Human capital (e.g., education, skills, training) • Financial capital (e.g., loans, savings) • Social capital (e.g., networks, mentors) • Physical capital (e.g., land, machinery) | No |  | Percentage | People | Gender | Numerator: # of women who have gained improved access to resources such as financial services, social networks, or physical assets. Denominator: total number of women who were targeted or reached by the project. |  | External consultant | Women in the target area | Baseline, midterm, and Endline | TBC | In Progress |  | External consultant
LL&VT | Output/Result | Number of support provided to women entrepreneurs. Target for tranche 1: 45 (L25+VN20) |  | Number of training that provided to women entrepeneirs | Yes |  | Numberic | Support/Training | n/a | # of trainings provided to communities and schools |  | MEAL and PO | Number of training conducted | Quaterly | Attandance sheet and activity report | Done | MEAL team | MEAL team
LL&VT | Output/Result | Number of Business development plans developed. |  | Number of business plans are developed from the villagers and students who joined the training | Yes |  | Numberic | Plan | n/a | Count the number of business plan developed |  | MEAL and PO | Count the number of business plan developed | Quaterly | Activity report | Done | MEAL team | MEAL team

## 4.2 - INDICATORS MONITORING
TRACKING INDICATORS
UPDATE DATE | [5 empty] | formula to be set for each indicator at the start of the project |  | duration to suit your project | [23 empty] | COMMENTS / QUALITATIVE INFORMATION ON THE SITUATION (to be completed by the project manager at the monthly follow-up meeting) | REGIONAL MANAGEMENT FEEDBACK (to be completed by regional coordinator in response to comments, questions, suggestions, solutions...) | PARTICIPANTS FEEDBACK
DESCRIPTION OF THE INDICATOR | [7 empty] | DATA COLLECTION FOLLOW-UP
OBJECTIVES/RESULTS(logical framework link) | INDICATOR LABEL (=column C - tab 4.1)Auto-fill | Calculation method (=column K- tab 4,1)Automatic filling | Internal / External (= lessor/contractor) | Baseline | Target | Achieved (automatic) | % complete (automatic) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
| % of young women targeted by GEVEE will experience an increase in resources and improved attitudes towards working women | Number of young women who have gained access to resources such as education, training, financial support, mentorship, or other opportunities that enhance their capabilities for employment. AND, those who have have a positive change in their attitudes towards working women, such as increased support, acceptance, or reduced gender-based biases agaist baseline value. | External | Checking | 60% | 87% | 145% | [26 empty] | The tracking system is good but can we adjust to fit in the reality-example, we summary by quarter not month.
| By end of the project, % of GEVEE women will have increased access to financial, social or physical capital for personal advancement (adapted from ICRW4 ) | Numerator: # of women who have gained improved access to resources such as financial services, social networks, or physical assets. Denominator: total number of women who were targeted or reached by the project. | External | Checking | 30% | 92% | 306.7%
| Number of support provided to women entrepreneurs. | # of trainings provided to communities and schools | Internal | Checking | 8 | 8 | 100%
| Number of Business development plans developed. | Count the number of business plan developed | Internal | Checking | 16 | 21 | 131.2%
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
[6 empty] | 0 | #DIV/0!
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## 4.3 BENEFICIARY MONITORING
BENEFICIARY FOLLOW-UP
UPDATE DATE
Target populations / people directly concerned |  |  |  | Q1 | [8 empty] | PARTICIPANTS FEEDBACK
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 12
F | 12
TOTAL | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | Q1
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 10
F | 10
TOTAL | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people directly concerned |  |  |  | Q2
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 0
F | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | Q2
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 10
F | 10
TOTAL | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people directly concerned |  |  |  | Q3
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | Q3
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people directly concerned |  |  |  | Q4
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | Q4
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DUPLICATE THE TABLES AS MANY TIMES AS NECESSARY ACCORDING TO THE TOTAL NUMBER OF QUARTERS IN YOUR PROJECT - UPDATE THE FORMULAS IN THE TABLE BELOW TO ¨TAKE INTO ACCOUNT ALL THE QUARTERLY TABLES ADDED
AUTOMATIC FILLING but formulas to adjusted if needed
Target populations / people directly concerned |  |  |  | TOTAL
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
... | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
... | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add rows below + check that new rows are included in the total below) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | TOTAL
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
... | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
... | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add rows below + check that new rows are included in the total below) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A13: ====== ID#AAABlHVwlT4 darnaudet valerie (2025-06-03 15:54:47) formulas needs to be adjusted depending on how many criterias of disaggregation you want - add lignes within sum columns if needed
Note on A24: ====== ID#AAABlHVwlT8 darnaudet valerie (2025-06-03 15:57:03) formula to be adjusted if needed / same model as previously
Note on A37: ====== ID#AAABlHVwlUA darnaudet valerie (2025-06-03 15:57:13) formula to be adjusted if needed / same model as previously
Note on A48: ====== ID#AAABlHVwlUE darnaudet valerie (2025-06-03 15:59:47) formula to be adjusted if needed / same model as previously
Note on A61: ====== ID#AAABlHVwlUI darnaudet valerie (2025-06-03 16:00:18) formula to be adjusted if needed / same model as previously
Note on A72: ====== ID#AAABlHVwlUM darnaudet valerie (2025-06-03 16:00:22) formula to be adjusted if needed / same model as previously
Note on A85: ====== ID#AAABlHVwlUQ darnaudet valerie (2025-06-03 16:00:29) formula to be adjusted if needed / same model as previously
Note on A96: ====== ID#AAABlHVwlUU darnaudet valerie (2025-06-03 16:00:34) formula to be adjusted if needed / same model as previously
Note on A112: ====== ID#AAABlHVwlUY darnaudet valerie (2025-06-03 16:00:47) formula to be adjusted if needed / same model as previously
Note on A123: ====== ID#AAABlHVwlUc darnaudet valerie (2025-06-03 16:00:54) formula to be adjusted if needed / same model as previously

## 5 - BUDGET IMPLEMENTATION MONIT
BUDGET MONITORING | [5 empty] | Currency/Eur conversion rate in H1 | [34 empty] | possible code red if negative - conditional formatting
UPDATE DATE | [41 empty] | Adjust the number of columns to suit your needs | Set up the formula according to the % of assignment in conjunction with the administrative manager
DESCRIPTION |  |  |  | BUDGET (filled in at the start of the project) | [5 empty] | BUDGET MONITORING (actual project expenditure verified with administrative manager) | [15 empty] | PREVISIONAL MONITORING (planning future expenses) | [15 empty] | DONOR /FINANCIAL MONITORING - TO DATE |  |  |  | COMMENTS / QUALITATIVE INFORMATION (to be completed by the project manager during the reconciliation meeting with the administrative manager) | REGIONAL MANAGEMENT FEEDBACK (to be completed by regional coordinator in response to comments, questions, suggestions...) | PARTICIPANTS FEEDBACK
Project codeCode provided by administrative manager | Local activity codeCode provided by administrative manager | Budget line manager (Who?) | Budget lines (donor format or own funds - identical to budget formulation) | NB (Unit) | Freq (M) | Unit Cost - Project currency | Uni cost EUR (auto calculation) | Total Cost Project currency | Total Cost EUR (auto calculation) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | TOT REALIZED (local currency) | TOTAL REALIZED EUROS | % completed to date | Balance at date | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | TOT ACTUAL + PLANNED local currency | TOTAL ACTUAL + FORECAST EUROS | Landing on overall budget | Balance on overall budget | Donor code 1 | Donor code 2 | Donor code 3 | Donor code 4
|  |  |  | 3 | 3 | 150 | 0 | 1350 | 0 | BUDGET MONITORING (actual project expenditure verified with administrative manager) M1: 450; BUDGET MONITORING (actual project expenditure verified with administrative manager) M2: 0; BUDGET MONITORING (actual project expenditure verified with administrative manager) M3: 150; BUDGET MONITORING (actual project expenditure verified with administrative manager) M4: 0; BUDGET MONITORING (actual project expenditure verified with administrative manager) M5: 0 | 600 | 0 | 44.44% | 750 | [11 empty] | 450 | 1050 | 0 | 77.78% | 300 | 375
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[38 empty] | 0 | 0 | #DIV/0! | 0 | 0
[38 empty] | 0 | 0 | #DIV/0! | 0 | 0
[38 empty] | 0 | 0 | #DIV/0! | 0 | 0
[38 empty] | 0 | 0 | #DIV/0! | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on H4: ====== ID#AAABicsSqCA (2025-04-24 09:01:05) =H*H1 -darnaudet valerie
Note on J4: ====== ID#AAABicsSqB8 (2025-04-24 09:01:05) =I*H1 -darnaudet valerie
Note on AP4: ====== ID#AAABicsSqCE (2025-04-24 09:01:05) =AO*H1 -darnaudet valerie
Note on AT4: ====== ID#AAABicsSqCQ (2025-04-24 09:01:05) =colonne Z * X% -darnaudet valerie