## 0 - Guide (hidden)
USER GUIDE
MONITORING & EVALUATION DASHBOARD
This dashboard is an experimental tool. The pilot phase of the M&E deployment should enable us to verify its usefulness and functionality. The aim is to test it, so that it can be optimized and improved. What is not useful will be removed, and what is missing will be added. Experimentation is therefore part of a learning process for the tool itself. It is not, therefore, a version that claims to be definitive and set in stone.
Tabs | Objectives | Update (recommended) | PARTICIPANTS FEEDBACK
Tab 0 - Guide | Explanatory notes on using the project dashboard | revision/updating of the SE guide - produced by the International Division
Tab 1 - Project Information | This tab provides an overview of the main features of the project, including the actors/partners involved in the project, as well as the direct and indirect stakeholders/beneficiaries. It recalls the project's logical framework. | In the event of a significant change to the project (Cost extension, No Cost, delay, major reorientation of activity)
Tab 2 - Review & Analysis | This tab provides a visual summary (diagrams) of the project’s main indicators as well as project management and monitoring information. It is made up of two sections: On the left: a section dedicated to project data in terms of direct beneficiaries, indirect beneficiaries, confirmed persons, and key indicators. The beneficiary chart is automated but can be adjusted or modified if needed. However, regarding the key indicators—particularly those that can be aggregated at the international level—pre-configuration is not possible because it depends on the project’s choices. Therefore, configuration must be carried out at the beginning of the project. On the right: a section dedicated to project management data, corresponding more to metadata. These allow the tracking of project implementation. All formulas are pre-configured, and the data are linked to different tabs (Tab 3 – Action Plan; Tab 4.2 – Indicators Monitoring; Tab 5 – Budget Implementation Monitoring). They update automatically depending on changes made in the “3_Action Plan,” “4.2_Indicators Monitoring,” and “5_Budget Implementation Monitoring” tabs. Next to each indicator, a space (white box) is dedicated to narrative analysis. This box must be filled in manually after collective analysis discussions with the project team. These elements are essential to explain, provide context, and justify certain data, considering that the dashboard will be shared with regional coordination. Finally, check whether it is necessary to keep an annual record/history. Otherwise, the tab will continue to update throughout the project without retaining past data—so it may be necessary to make regular copies. | Quarterly
Tab 3 - Action Plan | This tab must be filled in and aligned with the project action plan. It will identify when activities are due to be implemented during the life of the project, and will allow you to track the completion of activities as they are carried out. It should be reviewed and updated in parallel with monthly internal reporting. For each activity line, there is a dialogue area (column AM; AN; AO). Project teams can provide explanatory information on the status of certain activities, and identify the decisions taken in the next column. Regional coordination can provide feedback, recommendations and questions in the last column.) This tab requires settings at the start of the project: Column C: note each activity and sub-activity of your action plan on each line. You can detail your activities as much as you like. Column D: activity target, if relevant - some activities may not have a target, in which case leave it blank. Column E: unit - specify the unit of the activity: sessions; people.... Columns F and G are autimatic and already parameterized. Column H: this column links to the budget line of the activity line and refers to data in tab 5. It must be set at the start of the project. Columns K and L: the planned line must be filled in with the forecast dates in DD/MM/YYYY format; the completed line is filled in progressively in the same format. Column I: Status is a drop-down list. It must be filled in following a monthly team dialogue on the status of the activity. Time settings: the number of months in the project must be adjusted (on the screen it is 24 months, but you can add or delete columns according to the duration of your project). The dates in rows 3 and 4 of the month columns must be updated to reflect the dates of your project. You can add quantity concepts in each cell, which will enable you to calculate the achievement of the target in terms of activity. | Monthly
Tab 4.1 - M&E Plan | This tab contains the indicators from the M&E plan (narrative support accompanying the dashboard). It is used to define the project's indicators, their definition, and the collection tools....It is filled in at the start of the project. This is an informative tab, and will not be modified except in the event of a major change to the project that would impact the M&E indicators. | In the event of significant changes to the project and project indicators
Tab 4.2 - Indicators Monitoring | This tab reproduces the indicators from the M&E plan, tab 4.1. Columns B & C are automatic. It facilitates monthly data recording. At the same time, you don't have to fill in each indicator every month. It includes automatic formulas for tracking the quantitative progress of each indicator. The pre-existing parameters are basic (sums) and must be updated at the start of the project according to the calculation mode for each indicator. The calculation mode is set in column G at the start of the project. The figures entered can be linked to Tab 2 - Balance sheet and analysis.
Tab 4.3 Beneficiary Monitoring | This tab allows you to track beneficiaries by profile, using the harmonized ACTEI GPMF format. There is a table of direct beneficiaries and a table of indirect beneficiaries by quarter. At the bottom, a total table automatically calculates the totall of all quarters. In the basic framework, 4 quarters are parameterized. Additional tables can be added if required. In this case, the total table is revised to adjust the calculation formulas. This total table is linked to the 2-balance and analysis tab.
Tab 5 - Budget Implementation Monitoring | This tab contains the detailed budget for each project and the monthly forecast. It must be completed each month by the project manager (pre-filling in known information) in collaboration with the administrative manager (reconciliation) according to the expenses incurred. A monthly reconciliation is carried out to compare operational and accounting data. One section is dedicated to qualitative note-taking, column AY and AZ. It consists of 3 sections: 1 section for the initial budget forecast, corresponding to the project budget at the time of conception/ donor budget. Budget line codes must be supplied by the administrative manager. This budget is filled in at the start of the project. 2nd section dedicated to the actual budget per month. Automatic calculations are set up to track line realizations. This section is updated every month. 3rd section dedicated to the new forecast, i.e. the remaining months. Automatic calculations are set up to monitor line completion. Automatic calculations are set up to track line completion. This section is updated every month. Please note: this tab remains a project management and monitoring tool. It is intended to facilitate the operational reading of the project. It is in no way an accounting tool. Only the accounting tool (ERP5) is used for financial reporting. | Monthly

## Sum#_Goal_Outcome_Out_Activ (hidden)
Summary Logical Framework for CCOSC
# of Logical | Measure of logical | Activity of logical
1 | Goal
| Goal | Marginalized, out of school children in Cambodia will have access to equitable, quality, and relevant primary education.
3 | OUTCOME
| OUTCOME 1: | OOSC have increased equitable access to primary education opportunities
| OUTCOME 2: | OOSC have received primary education with improved quality and relevance
| OUTCOME 3 | OOSC duty bearers and rights holders have strengthened their mutual accountability
6 | Output
Output 1.1 Expanded spaces for OOSC to learn
Output 1.2 Greater support for schooling of OOSC
Output 2.1 Enriched learning opportunities for OOSC
Output 2.2 Increased educational capacity of key actors
Output 3.1 Enhanced community engagement in OOSC issues
Output 3.2 Strengthened advocacy for OOSC issues
18 | Activity
Activity 1.1.1: a) Build 20 new schools , b) build new 130 classrooms, c) refurbish 960 classroms and d) refurbish 40 schools for 18,2000 OOSC
Activity 1.1.2: Sponsor 1,108 non-formal education activities for 11,108 OOSC
Activity 1.1.3: Establish and/or expand 4,478 MLE, AL, inclusive education, and flexible classes for 29,056 OOSC
Activity 1.2.1: Provide 17,00 OOSC with in-kind study support & services for learning
Activity 1.2.2: Award 17,000 OOSC with scholarships for learning
Activity 1.2.3: Assist 3,765 OOSC families (5,645 OOSC) with livelihood and in-kind support and services
Activity 2.1.1: Create or revise 200 relevant learning curricula and/or education tools
Activity 2.1.2: Carry out 383 professional development activities for 5,745 teachers
Activity 2.1.3: Provide enhanced learning opportunities in 1,023 schools for 42,996 OOSC
Activity 2.2.1: Develop school management plans for 511 schools
Activity 2.2.2: Stage 256 capacity building activities for 3,072 education actors
Activity 2.2.3: Implement child friendly school measures in 511 schools
Activity 3.1.1: Launch 2,433 awareness / enrolment campaigns in communities with OOSC
Activity 3.1.2: Organize 2,086 events for 27,118 parents, youth and CBO members to advocate for OOSC issues
Activity 3.1.3: Conduct school accountability audits in 1,534 schools.
Activity 3.2.1: Convene 32 forums to share learning and advocate for OOSC issues
Activity 3.2.2: Participate in 16 policy dialogues on OOSC issues
Activity 3.2.3: Share 8 documentation or reseach efforts on OOSC issues with 800 individuals
Noted | Pos: | The M&E project officer (PO)
On Sheet: 4.1 - M&E Plan on Column A
For selected have 3 indicators:
1.ECCE :Early Children Care and Education
Focus on supporting young children (ususally ages 0-5 with nurturing care ,learning, and development before they enter primmary scchool.
2.AQE : Access and Quality of Education
Aim to ensure children not only get into school but also receive a meaningful , high-quality education.
3.LL& VT ; Lifelong Learning and Vocational Training
Supports older children and youth with skills for life an work,including non-formal education and job training.
Questions:
* For the project : CCOSC ,It schould count for AQE for all indicator?

## 1 - PROJECT INFORMATION (hidden)
UPDATE DATE
PROJECT INFORMATION | [12 empty] | PARTICIPANTS FEEDBACK
I- General information
Program/project title | Program/project title
ERP5 code | AFR008
Priority themes (is it possible to have more than one priority theme in a project? if not, just one box to answer the question)
Key themes (several key themes possible)
Cross-cutting themes ( several key themes possible)
General objective of the project | Overall project objective (as stated in the logical framework)
Intervention area(s) | Specify the location of the intervention area (regions, communes, neighborhoods...)
Project target group(s) | Specify the people concerned, the project's target populations (list the main categories - as mentioned in the synoptic sheet)
Project dates & duration | Project start date |  | 2020-01-01 | Project end date |  | 2021-12-31 |  | Duration |  | X months
New phase of a previous project? | [Select] |  | If yes, please specify previous projects (name, dates, lessor...)
II- Budget
Budget | Currency |  | Euros | Total |  | 500000 |  | Amount spent (at update date) |  | 200000
Lessor | Lessor's name |  |  | Amount of subsidy |  | Amount and currencies |  | Contract dates |  | DD/MM/YYYY |  | DD/MM/YYYY
- If co-financed - Lessor 1 | Lessor's name |  |  | Amount of subsidy |  | Amount and currencies |  | Contract dates |  | DD/MM/YYYY |  | DD/MM/YYYY
Add as many lines as necessary
III- ACTEI contact persons
Project contact | Name | First name | Position | e-mail | phone
IV- Partners
Consortium project? | Yes |  | If yes, specify who the lead is :
Project with operational partners? | Yes |  | If yes, please specify the partner information below.
Implementation partners | Nature/Profile of partner |  |  | Project role or category? |  | Signature of agreement |  | Comments
Actor 1 |  |  |  | Institutional (State) -generally not only one project
Actor 2 |  |  |  | Technical and Financial Partner
Actor 3 |  |  |  | Operational (local NGO; CSO...)
Actor 4
Actor 5
Actor 6
Actor 7
Actor 8
Actor 9
Actor 10
Add as many lines as necessary
TOTAL PARTNERS BY CATEGORY (automatic calculation) | Institutional | 1 | PTF | 1 | Operational | 1
V - Target populations / People concerned / Beneficiaries (GPMF classification)
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
VI - LOGICAL FRAMEWORK OF THE PROJECT (as mentioned in the synoptic sheet)
Overall objectives
Specific objectives (add rows if necessary)
Main expected results (add rows if necessary)
Main activities (add rows if necessary)

## 4.1 - M&E Plan
MONITORING AND EVALUATION PLAN - Presentation of indicators
Orange columns - taken from indicator database / blue columns - project-specific information | [18 empty] | PARTICIPANTS FEEDBACK
Description: Identification of the thematic priority in line with the ACTEI 2025-2029 strategy. | Description: Indicates the level of the results chain with which the indicator is associated. (Impact/effects/products/activities) | Specific formulation of the indicator | Description: Name or title of the indicator. It summarizes in a few words the objective or dimension being measured. Example: Enrolment rate for children aged 6 to 11. | Description: Provides a detailed and precise explanation of the indicator, clarifying its components, scope and purpose. Example: Percentage of pupils completing primary education with sufficient literacy and numeracy skills. | Description: indicates whether an indicator can be aggregated across the various ACTEI projects. This means that the data collected for this indicator can be added up over several time periods or between several projects to obtain a relevant overall total. | Description: Identification of the key action in line with the ACTEI 2025-2029 strategy. | Description: Specifies the nature of the data collected. Options: Numeric: A raw value (e.g. 500 schools renovated). Percentage: A proportion (e.g. 80% of teachers trained). Categorical: Classified data (e.g. low/medium/high). | Description: The unit of measurement used for the indicator. Example: people, schools, projects, communities | Description: Levels or categories according to which data can be broken down for finer analysis. Example: Gender, age range, geographic area | Description: Explains how the indicator value is obtained, detailing the calculation steps or formulas. Example: Number of children attending school divided by the total number of eligible children. | Project- and context-specific uses | Specify the people and/or team of partners who will collect the information | Specify from whom the information will be collected, who is the source of the information, who holds it? | How often or when should training be collected? | What tool, method or source of verification should be used to collect the information? | Is the tool ready yet? | Who is responsible for entering data into the dashboard? | Who will participate in the analysis of this data?
Thematic priority | Perimeter | Indicator label - project-specific | Indicator label (indicator bank formulation - if relevant) N.A if the indicator does not refer to any bank indicator and is specific to the project | Indicator definition | Cumulative ACTEI | Key action | Type of indicator | Observed unit | Disaggregations | Calculation methodology | For the project | Who collects? | Who holds the information (from whom is the data collected?) | When (collection frequency) | Which tools? | Tool status | Who enters the data into the dashboard? | Who analyzes? |  | Code for count in 4.2
AQE | Impact | Goal1:Number of new OOSC who are enrolled in primary education programs | Enrolment rate of OOSC in primary education programs | Categories of Out of School Children have 5 such as: 1-Children who do not have access to a school : This includes children from poor and remote areas of the country where geography and lack of resources mean that there is no available school for them to attend. It also includes migrant children, child laborers and those living in extreme poverty in rural or isolated areas 2- Children who have access to school but who are not enrolled : This group includes ethnic minority groups where language barriers prevent their access to education. It also includes students that because of special needs (i.e. learning difficulties) or other pul factors (i.e. child labor) are not attending school. Importantly, this category also includes young girls who suffer from prevailing cultural attitudes requiring them to work at home or marry early, as wel as the dangers of school gender-based violence. 3.Children who have access and have enrolled in school but who do not attend: This category includes children with disabilities who may enrol in school but then find that their schools are i l-equipped to deal with their special pedagogical and accessibility needs. It can also include mobile populations or children with severe family difficulties or domestic violence. This category also includes children who have high absenteeism (greater than 90%) and/ or do not attend school for whatever reason. 4.-Children who have dropped out of school: This includes street children in Cambodia who face unique chalenges of poor health, exploitation and abuse. It also includes overage children who have falen behind due to late enrolment and high repetition, girls who are especialy vulnerable due to early marriage, pregnancy and other gendered norms that pul them out of school, and children of ethnic minorities who find it difficult or impossible to adjust to the national language of instruction. 5.-Children who are in emergency or crisis situations: This category usualy applies in the case of natural disasters (e.g. flooding and landslides). During natural disasters, Consortium members wi l work with relevant partners to ensure appropriate responses to displaced children or those who have lost access to school due to natural disasters. This category also includes children who are not alowed to enrol in school. This population includes foreign nationals who because they are immigrants to Cambodia often do not have the required identification documentation for school enrolment. Source: According to the definition provided by Educate A Child (EAC), 2018 Funding Proposal, the Cambodian Consortium for Out of School Children (CCOSC), led by Aide et Action International - Cambodia.) | Yes | N/A | Quantitative | Children | Gender, Province, urban / rural, age, school, grade, ethnicity, category of OOSC | Total number of new children enrolled = sum of children enrolled. Gather the data from each partner and combine it into one file using the CEMISE system | CCOSC | Team of Partners | Team of Partners | Semester | CEMIS System: Documents Support (Marginalized out of school children identification form ,Birth certificate , Student list) | Done | Program Manager/Meal Team | M&E Manager |  | 2
AQE | Outcome/Effect | OUTCOME1.1: Completion rate of newly enrolled OOSC | Completion rate of newly enrolment OOSC | "Completion rate" means the number of newly enrolled OOSC completing the last year (Grade 6) of primary education, expressed as a percentage of the number of OOSC completing grade 6 divided by the total Number of OOSC enrolled in Grade 6 for that year. (MOEYS definition; "Full course" can refer to Grades 1-6, 2-6, 3-6, or 4-6 depending on when the OOSC enrols. | No | N/A | Qualitative | Children | Gender, Province, urban / rural, ethnicity | Percentage of the number of OOSC completing grade 6 divided by the total Number of OOSC enrolled in Grade 6 for that year. (MOEYS definition; "Full course" can refer to Grades 1-6, 2-6, 3-6, or 4-6 depending on when the OOSC enrols. | CCOSC | Team of Partners | Team of Partners | Annual | CEMIS System: Documents Support (Marginalized out of school children identification form ,Birth certificate , Student list) | Done | Program Manager/Meal Team | M&E Manager |  | 2
AQE | Output/Result | Output 1.1 Expanded spaces for OOSC to learn |  |  |  | N/A | [13 empty] | 2
AQE | Activity | 1.1.1a: Number of new schools constructed | New schools construction | The total count of newly built educational facilities (schools) within a specified geographic area and time period. This includes schools constructed from the ground up and officially opened for use | Yes | N/A | Quantitative | New School | Province, type of structure | CEMIS | CCOSC | Team of Partners | Team of Partners | Semester | List new record school,Contract, Financial report, Aggrement, Picture | Done | Program Manager/Meal Team | M&E Manager |  | 2
AQE | Activity | 1.1.1b: Number of new classrooms constructed | New classrooms construction | The total number of individual classroom units built and completed within a specified geographic area and time period. | Yes | N/A | Quantitative | New Classroom | Province, school name | CEMIS | CCOSC | Team of Partners | Team of Partners | Semester | List new record school,Contract, Financial report, Aggrement, Picture | Done | Program Manager/Meal Team | M&E Manager |  | 2
AQE | Activity | 1.1.1c: Number of classrooms refurbished | 1.1.1c: Number of classrooms refurbished | The total number of existing classroom units that have undergone significant renovation or improvement within a specified geographic area and time period. Refurbishment may include structural repairs, upgrades to lighting, ventilation, flooring, furniture, or educational technology, aimed at enhancing the learning environment. | Yes | N/A | Quantitative | Classroom Refurbish | Province, type of refurbishment, school name | CEMIS | CCOSC | Team of Partners | Team of Partners | Semester | List new record classrooms refurbished,Contract, Financial report, Aggrement, Picture | Done | Program Manager/Meal Team | M&E Manager |  | 2
AQE | Activity | 1.1.1d: Number of schools refurbished | Number of schools refurbish | The total number of existing school facilities that have undergone substantial renovation or improvement within a specified geographic area and time period. This includes upgrades aimed at enhancing safety, functionality, and the overall learning environment, without constructing entirely new buildings. | Yes | N/A | Quantitative | School Refurbish | Province, type of refurbishment, school name | CEMIS | CCOSC | Team of Partners | Team of Partners | Semester | List record classrooms refurbished ,Picture | Done | Program Manager/Meal Team | M&E Manager |  | 2
AQE | Activity | 1.1.2.Number of OOSC participating in nonformal education programs or activities | Number of OOSC participant in nonformal education programs | "A non-formal course or program" means a program or course providing non-formal education in line with MoEYS standards; this can include re-entry or remedial classes which are designed for children who have been out of school for an extended time period; "completing" means the OOSC has achieved 90Percentage attendance and has successfully passed exit examinations, if any; "activities" = outside the classroom, can include sports activities, mobile clinics, literacy classes, community learning centers, other community educational offerings. The assumption is that NFE course, program, or activity is a bridge to enrolment in the formal system. | No | N/A | Quantitative | Children ,Program Type | Gender, Province, urban / rural, age, school, grade, ethnicity, program type | CEMIS | CCOSC | Team of Partners | Team of Partners | Semester | Student list, Work Plan, Pre-Post test, Narrative Report | Done | Program Manager/Meal Team | M&E Manager |  | 2
AQE | Activity | 1.1.3:Number of newly enrolled OOSC benefitting from MLE, AL, inclusive, or flexible classes | Number of OOSC benefitting from MLE, AL, inclusive, or flexible classes | "MLE" = multi-lingual classes are classes provided in native language for non-Khmer speakers; "AL" = accelerated learning, or classes designed to deliver the content of one academic year in a shorter time frame; "inclusive education class" = separate or integrated class for children with physical or mental disabilities; "flexible" means formal education classes provided at a time which is more convenient to OOSC (i.e. afternoon sessions); "benefitting" means these classes helped OOSC to enrol and to stay enrolled. The assumption is that these classes will help OOSC to enrol and stay enrolled. | Yes | N/A | Quantitative | Children , Class Type | Gender, Province, urban / rural, age, ethnicity, school, class type | CEMIS | CCOSC | Team of Partners | Team of Partners | Semester | Student list, Work Plan, Pre-Post test, Narrative Report | Done | Program Manager/Meal Team | M&E Manager |  | 2
| Output/Result | Output 1.2 Greater support for schooling of OOSC | Support for schooling of OOSC |  |  | N/A | [13 empty] | 2
AQE | Activity | 1.2.1:Number of newly enrolled OOSC who receive in-kind study support or services | Number of OOSC receive in-kind study support or services | "in-kind study support" means non financial support in the way of bicycles, school supplies, nutritional aids, assistive devices; "services" means referrals to health centers or other social support. It is different from Indicator 1.2.2 which measures financial scholarships only given to a different population of OOSC. The assumption is that OOSC who receive this support will enrol in formal schooling. | Yes | N/A | Quantititive | In-kind study support | Gender, Province, urban / rural, school, age, grade, ethnicity | CEMIS | CCOSC | Team of Partners | Team of Partners | Semester | CEMIS System: List record OOSC received in-kind study, pictures | Done | Program Manager/Meal Team | M&E Manager |  | 2
AQE | Activity | 1.2.2:Number of newly enrolled OOSC who receive scholarships | Number of OOSC receive scholarships | "Scholarships" = money given to OOSC to be used for their educational expenses and costs while they are attending school with more than 90% attendance. It is not the same as Indicator 1.2.1 which measures non-financial assistance to OOSC only given to a different population of OOSC. The assumption is that OOSC who receive this support will enrol in formal schooling. | Yes | N/A | Quantititive | Scholarships | Gender, Province, urban / rural, age, school, grade, ethnicity | CEMISE |  | Team of Partners | Team of Partners | Semester | CEMIS System: List record OOSC received scholarships ,pictures | Done | Program Manager/Meal Team | M&E Manager |  | 2
LL&VT | Activity | 1.2.3:Number of newly enrolled OOSC whose families receive livelihood support & services | Number of OOSC families receive livelihood support & services | "Livelihood support and services" = technical assistance, money or stipends, referral to other programs, in-kind inputs, or other similar support to help OOSC families generate their own income to send their children to school. The assumption is that these families will be able to send their children to school after they receive support from the project or that this support helps them to keep their children in school once they are already enrolled. The multiplier of 1.5 child per benefitting family has been used. | Yes | N/A | Quantititive | Family | Gender, Province, urban / rural, age, school, grade, ethnicity | CEMISE | CCOSC | Team of Partners | Team of Partners | Semester | CEMIS System: Family identification form | Done | Program Manager/Meal Team | M&E Manager |  | 2
Note on B6: ====== ID#AAABqLU6mR8 Chanthorn HENG (2025-08-28 10:09:08) In proposal II,don't have indicator meausure on impact ,it has measure on " Goal"
Note on C15: ====== ID#AAABqLU6mR4 Chanthorn HENG (2025-08-28 10:09:08) for only output ,for other items don't have.

## 4.2 - INDICATORS MONITORING
TRACKING INDICATORS
UPDATE DATE | [10 empty] | formula to be set for each indicator at the start of the project |  | duration to suit your project | [23 empty] | COMMENTS / QUALITATIVE INFORMATION ON THE SITUATION (to be completed by the project manager at the monthly follow-up meeting) | REGIONAL MANAGEMENT FEEDBACK (to be completed by regional coordinator in response to comments, questions, suggestions, solutions...) | PARTICIPANTS FEEDBACK
DESCRIPTION OF THE INDICATOR | [12 empty] | DATA COLLECTION FOLLOW-UP
OBJECTIVES/RESULTS(logical framework link) | INDICATOR LABEL (=column C - tab 4.1)Auto-fill | Calculation method (=column K- tab 4,1)Automatic filling | Internal / External (= lessor/contractor) | Baseline | When | Y1 | Y2 | Y3 | Y4 | Target | Achieved (automatic) | % complete (automatic) | S1 | S2 | S3 | S4 | S5 | S6 | S7 | S8 | S9 | S10 | S11 | S12 | S13 | S14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
2 | Goal1:Number of new OOSC who are enrolled in primary education programs | Total number of new children enrolled = sum of children enrolled. Gather the data from each partner and combine it into one file using the CEMISE system | External | N/A | Semester | 11640 | 40739 | 40739 | 23279 | 116397 |  |  | DATA COLLECTION FOLLOW-UP S1: 14549.625; DATA COLLECTION FOLLOW-UP S2: 14549.625; DATA COLLECTION FOLLOW-UP S3: 14549.625; DATA COLLECTION FOLLOW-UP S4: 14549.625; DATA COLLECTION FOLLOW-UP S5: 14549.625; DATA COLLECTION FOLLOW-UP S6: 14549.625; DATA COLLECTION FOLLOW-UP S7: 14549.625; DATA COLLECTION FOLLOW-UP S8: 14549.625 | N/A | N/A
2 | OUTCOME1.1: Completion rate of newly enrolled OOSC | Percentage of the number of OOSC completing grade 6 divided by the total Number of OOSC enrolled in Grade 6 for that year. (MOEYS definition; "Full course" can refer to Grades 1-6, 2-6, 3-6, or 4-6 depending on when the OOSC enrols. | External | N/A | Annual | 85% | 85% | 85% | 85% | 85% | 85% | 100% | DATA COLLECTION FOLLOW-UP S2: 85%; DATA COLLECTION FOLLOW-UP S4: 85%; DATA COLLECTION FOLLOW-UP S6: 85%; DATA COLLECTION FOLLOW-UP S8: 85% | N/A | N/A
2 | Output 1.1 Expanded spaces for OOSC to learn | 0 | [8 empty] | 0 | #DIV/0!
2 | 1.1.1a: Number of new schools constructed | CEMIS | External | N/A | Semester | 8 | 8 | 4 | 0 | 20 | 20 | 100% | DATA COLLECTION FOLLOW-UP S1: 4; DATA COLLECTION FOLLOW-UP S2: 4; DATA COLLECTION FOLLOW-UP S3: 4; DATA COLLECTION FOLLOW-UP S4: 4; DATA COLLECTION FOLLOW-UP S5: 2; DATA COLLECTION FOLLOW-UP S6: 2; DATA COLLECTION FOLLOW-UP S7: 0; DATA COLLECTION FOLLOW-UP S8: 0 | N/A | N/A
2 | 1.1.1b: Number of new classrooms constructed | CEMIS | External | N/A | Semester | 52 | 52 | 26 | 0 | 130 |  |  | DATA COLLECTION FOLLOW-UP S1: 26; DATA COLLECTION FOLLOW-UP S2: 26; DATA COLLECTION FOLLOW-UP S3: 26; DATA COLLECTION FOLLOW-UP S4: 26; DATA COLLECTION FOLLOW-UP S5: 13; DATA COLLECTION FOLLOW-UP S6: 13; DATA COLLECTION FOLLOW-UP S7: 0; DATA COLLECTION FOLLOW-UP S8: 0 | N/A | N/A
2 | 1.1.1c: Number of classrooms refurbished | CEMIS | External | N/A | Semester | 384 | 384 | 192 | 0 | 960 | 960 | 100% | DATA COLLECTION FOLLOW-UP S1: 192; DATA COLLECTION FOLLOW-UP S2: 192; DATA COLLECTION FOLLOW-UP S3: 192; DATA COLLECTION FOLLOW-UP S4: 192; DATA COLLECTION FOLLOW-UP S5: 96; DATA COLLECTION FOLLOW-UP S6: 96; DATA COLLECTION FOLLOW-UP S7: 0; DATA COLLECTION FOLLOW-UP S8: 0 | N/A | N/A
2 | 1.1.1d: Number of schools refurbished | CEMIS | External | N/A | Semester | 16 | 16 | 8 | 0 | 40 | 32 | 80% | DATA COLLECTION FOLLOW-UP S1: 8; DATA COLLECTION FOLLOW-UP S2: 8; DATA COLLECTION FOLLOW-UP S3: 8; DATA COLLECTION FOLLOW-UP S4: 8; DATA COLLECTION FOLLOW-UP S5: 0; DATA COLLECTION FOLLOW-UP S6: 0; DATA COLLECTION FOLLOW-UP S7: 0; DATA COLLECTION FOLLOW-UP S8: 0 | N/A | N/A
2 | 1.1.2.Number of OOSC participating in nonformal education programs or activities | CEMIS | External | N/A | Semester | 1108 | 3878 | 3878 | 2216 | 11080 | 7202 | 65% | DATA COLLECTION FOLLOW-UP S1: 554; DATA COLLECTION FOLLOW-UP S2: 554; DATA COLLECTION FOLLOW-UP S3: 1939; DATA COLLECTION FOLLOW-UP S4: 1939; DATA COLLECTION FOLLOW-UP S5: 1108; DATA COLLECTION FOLLOW-UP S6: 1108 | N/A | N/A
2 | 1.1.3:Number of newly enrolled OOSC benefitting from MLE, AL, inclusive, or flexible classes | CEMIS | External | N/A | Semester | 4726 | 9260 | 9260 | 5811 | 29057 | 0 | 0% | [24 empty] | N/A | N/A
2 | Output 1.2 Greater support for schooling of OOSC | 0 | [7 empty] | 0 | 0 | #DIV/0!
2 | 1.2.1:Number of newly enrolled OOSC who receive in-kind study support or services | CEMIS | External | N/A | Semester | 1700 | 5950 | 5950 | 3400 | 17000 | 17000 | 100% | DATA COLLECTION FOLLOW-UP S1: 850; DATA COLLECTION FOLLOW-UP S2: 850; DATA COLLECTION FOLLOW-UP S3: 2975; DATA COLLECTION FOLLOW-UP S4: 2975; DATA COLLECTION FOLLOW-UP S5: 2975; DATA COLLECTION FOLLOW-UP S6: 2975; DATA COLLECTION FOLLOW-UP S7: 1700; DATA COLLECTION FOLLOW-UP S8: 1700 | N/A | N/A
2 | 1.2.2:Number of newly enrolled OOSC who receive scholarships | CEMISE | External | N/A | Semester | 1700 | 5950 | 5950 | 3400 | 17000 | 17000 | 100% | DATA COLLECTION FOLLOW-UP S1: 850; DATA COLLECTION FOLLOW-UP S2: 850; DATA COLLECTION FOLLOW-UP S3: 2975; DATA COLLECTION FOLLOW-UP S4: 2975; DATA COLLECTION FOLLOW-UP S5: 2975; DATA COLLECTION FOLLOW-UP S6: 2975; DATA COLLECTION FOLLOW-UP S7: 1700; DATA COLLECTION FOLLOW-UP S8: 1700 | N/A | N/A
2 | 1.2.3:Number of newly enrolled OOSC whose families receive livelihood support & services | CEMISE | External | N/A | Semester | 565 | 1976 | 1976 | 1129 | 5646 | 5646 | 100% | DATA COLLECTION FOLLOW-UP S1: 282.5; DATA COLLECTION FOLLOW-UP S2: 282.5; DATA COLLECTION FOLLOW-UP S3: 988; DATA COLLECTION FOLLOW-UP S4: 988; DATA COLLECTION FOLLOW-UP S5: 988; DATA COLLECTION FOLLOW-UP S6: 988; DATA COLLECTION FOLLOW-UP S7: 564.5; DATA COLLECTION FOLLOW-UP S8: 564.5 | N/A | N/A
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0 | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on K13: ====== ID#AAABqLU6mSI Chanthorn HENG (2025-08-28 10:09:08) For life project=29,056 reported in Proposal ,Page61

## Code_Word (hidden)
Thematic priority | Full word
ECCE | Early Childhood Care and Education
Focuses on supporting young children (usually ages 0–5) with nurturing care, learning, and development before they enter primary school.
AQE | Access and Quality of Education
Aims to ensure children not only get into school but also receive a meaningful, high-quality education
LL&VT | Lifelong Learning and Vocational Training
Supports older children and youth with skills for life and work, including non-formal education and job training.

## 2 - REVIEW AND ANALYSIS (hidden)
REVIEW AND ANALYSIS
UPDATE DATE
PROJECT DATA |  |  |  | PROJECT MANAGEMENT / STEERING DATA
I- | MONITORING OF TARGET DIRECT BENEFICIARIES | MONITORING OF TARGET INDIRECT BENEFICIARIES | [date updated] Narrative indications / data analysis / explanations.... | I- | MONITORING THE IMPLEMENTATION OF ACTIVITIES
[date updated] Narrative indications / data analysis / explanations....
|  |  |  | Time-based activities | 0
|  |  |  | Late activities | 0
|  |  |  | Activities ahead of schedule | 0
|  |  |  | Completed activities | 0
Diagram linked to tab 4.3 - automatic, but profiles can be filtered by diagram data range |  | Diagram linked to tab 4.3 - automatic, but profiles can be filtered by diagram data range
Others forms of diagrams can also be set up |  | Others forms of diagrams can also be set up
II- | CUMULABLE INDICATORS ACTEI - to be configured for each project |  |  | II- | INDICATOR ACHIEVEMENT MONITORING
[date updated] Narrative indications / data analysis / explanations....
2.1 Indicator name |  |  |  | Indicators definitively achieved (100% or more) | 6
|  |  | "[date updated] Narrative indications / data analysis / explanations.... What was the subject of the satisfaction survey? - What does it mean for the project? | Indicators almost reached (75% and 100%) | 1
|  |  |  | Indicators partially achieved (50% and 75%) | 1
|  |  |  | Indicators only slightly achieved (25% and 50%) | 0
|  |  |  | Indicators not reached (0 and 25%) | 1
2.2Indicator wording
|  |  | "[date updated] | III- | BUDGET FOLLOW-UP
|  |  |  | To be completed manually according to the chapter headings in your project |  | [date updated] Narrative indications / data analysis / explanations....
|  |  |  | Budget chapter 1 :XXXXX | =Tab 5 - column Z Line corresponding to chapter total
|  |  |  | Budget section 2:XXXXX | =Tab 5 - column Z Line corresponding to chapter total
|  |  |  | Budget chapter 3: :XXXXX | =Tab 5 - column Z Line corresponding to chapter total
….
PARTICIPANTS FEEDBACK

## 3 - ACTION PLAN (hidden)
CHRONOGRAM |  | manual filling | [7 empty] | Setup at the start of the project |  |  | duration to suit your project
UPDATE DATE |  | Activities | TARGET | Unit | Total Actual | % Technical achievement | Budget %. | STATUS | Planned/ Realized | Start date | End date |  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | COMMENTS / QUALITATIVE INFORMATION ON THE SITUATION (to be completed by the project manager at the monthly follow-up meeting) | DECISION MAKING, MITIGATION MEASURES, SOLUTIONS PROPOSED (to be completed by the project manager during the monthly follow-up meeting) | REGIONAL MANAGEMENT FEEDBACK (to be completed by regional coordinator in response to comments, questions, suggestions, solutions...) | PARTICIPANTS FEEDBACK
[13 empty] | 2025-04-01 | 2025-05-01 | 2025-06-01 | 2025-07-01 | 2025-08-01 | 2025-09-01 | 2025-10-01 | 2025-11-01 | 2025-12-01 | 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-04-01 | 2026-05-01 | 2026-06-01 | 2026-07-01 | 2026-08-01 | 2026-09-01 | 2026-10-01 | 2026-11-01 | 2026-12-01 | 2027-01-01 | 2027-02-01 | 2027-03-01
[13 empty] | 2025-04-30 | 2025-05-31 | 2025-06-30 | 2025-07-31 | 2025-08-31 | 2025-09-30 | 2025-10-31 | 2025-11-30 | 2025-12-31 | 2026-01-31 | 2026-02-28 | 2026-03-31 | 2026-04-30 | 2026-05-31 | 2026-06-30 | 2026-07-31 | 2026-08-31 | 2026-09-30 | 2026-10-31 | 2026-11-30 | 2026-12-31 | 2027-01-31 | 2027-02-28 | 2027-03-31
LAUNCH PHASE |  | team recruitement | 10 | pers | 5 | 50% |  |  | Planned | 2025-04-01 | 2025-05-31 | - | bar: 2025-04-30 to 2025-05-31
[9 empty] | Realized | 2026-06-01 | 2025-12-31 | - | 2025-06-30: 5
|  | training of teachers | 3 | sessions | 3 | 100% |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | - | bar: 2025-08-31; 2025-10-31; 2025-12-31
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
IMPLEMENTATION PHASE | 1. OS/ RSEULATS - timer/logic frame settings
|  |  | 12 |  | 3 | 25% |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | - | 2025-04-30: 3
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned
Realized
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Realized |  |  | -
2.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
3.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
1.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
2.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
TRANSITION PHASE & CLOSING | 1.
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
[5 empty] | 0 | #DIV/0! |  |  | Planned |  |  | -
[9 empty] | Achieved |  |  | -
2.
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
[5 empty] | 0 | #DIV/0! |  |  | Planned
Achieved
Note on H2: ====== ID#AAABicsSqCM (2025-04-24 09:01:05) Paramétrage au début du projet : = onglet 5 colonne Z / identification de la ligne correspondante -darnaudet valerie
Note on I2: ====== ID#AAABlHVwlTw darnaudet valerie (2025-06-03 15:42:23) Manual entry – after discussion with the team. The notions of delay or being ahead of schedule must be meaningful, as they should trigger an alert. The goal is not to highlight minor delays of a few days that have no real impact on the project timeline.

## 4.3 BENEFICIARY MONITORING (hidden)
BENEFICIARY FOLLOW-UP
UPDATE DATE
Target populations / people directly concerned |  |  |  | Q1 | [8 empty] | PARTICIPANTS FEEDBACK
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 5
F | 12
TOTAL | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | Q1
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 10
F | 10
TOTAL | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people directly concerned |  |  |  | Q2
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 0
F | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | Q2
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 10
F | 10
TOTAL | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people directly concerned |  |  |  | Q3
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | Q3
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people directly concerned |  |  |  | Q4
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | Q4
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M
F
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
...
...
Add rows below + check that new rows are included in the total below)
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
DUPLICATE THE TABLES AS MANY TIMES AS NECESSARY ACCORDING TO THE TOTAL NUMBER OF QUARTERS IN YOUR PROJECT - UPDATE THE FORMULAS IN THE TABLE BELOW TO ¨TAKE INTO ACCOUNT ALL THE QUARTERLY TABLES ADDED
AUTOMATIC FILLING but formulas to adjusted if needed
Target populations / people directly concerned |  |  |  | TOTAL
Target populations / people directly concerned | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
... | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
... | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add rows below + check that new rows are included in the total below) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Target populations / people INdirectly concerned |  |  |  | TOTAL
Indirect target populations / people affected | Number of children in pre-school | Number of children in primary school | Number of children in lower secondary education | Number of children in upper secondary school | Number of young people in continuing or vocational training and/or entrepreneurship | No. of adults in vocational training and/or entrepreneurship | Number of out-of-school children | Number of parents/carers | Number of teachers & animators | Number of local authorities | Other members | Number of schools & centers
M | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
F | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sub-totals by disaggregation selected by the project (vulnerability, status, conditions, etc.)
... | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
... | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Add rows below + check that new rows are included in the total below) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on A13: ====== ID#AAABlHVwlT4 darnaudet valerie (2025-06-03 15:54:47) formulas needs to be adjusted depending on how many criterias of disaggregation you want - add lignes within sum columns if needed
Note on A24: ====== ID#AAABlHVwlT8 darnaudet valerie (2025-06-03 15:57:03) formula to be adjusted if needed / same model as previously
Note on A37: ====== ID#AAABlHVwlUA darnaudet valerie (2025-06-03 15:57:13) formula to be adjusted if needed / same model as previously
Note on A48: ====== ID#AAABlHVwlUE darnaudet valerie (2025-06-03 15:59:47) formula to be adjusted if needed / same model as previously
Note on A61: ====== ID#AAABlHVwlUI darnaudet valerie (2025-06-03 16:00:18) formula to be adjusted if needed / same model as previously
Note on A72: ====== ID#AAABlHVwlUM darnaudet valerie (2025-06-03 16:00:22) formula to be adjusted if needed / same model as previously
Note on A85: ====== ID#AAABlHVwlUQ darnaudet valerie (2025-06-03 16:00:29) formula to be adjusted if needed / same model as previously
Note on A96: ====== ID#AAABlHVwlUU darnaudet valerie (2025-06-03 16:00:34) formula to be adjusted if needed / same model as previously
Note on A112: ====== ID#AAABlHVwlUY darnaudet valerie (2025-06-03 16:00:47) formula to be adjusted if needed / same model as previously
Note on A123: ====== ID#AAABlHVwlUc darnaudet valerie (2025-06-03 16:00:54) formula to be adjusted if needed / same model as previously

## 5 - BUDGET IMPLEMENTATION MONIT (hidden)
BUDGET MONITORING | [5 empty] | Currency/Eur conversion rate in H1 | [34 empty] | possible code red if negative - conditional formatting
UPDATE DATE | [41 empty] | Adjust the number of columns to suit your needs | Set up the formula according to the % of assignment in conjunction with the administrative manager
DESCRIPTION |  |  |  | BUDGET (filled in at the start of the project) | [5 empty] | BUDGET MONITORING (actual project expenditure verified with administrative manager) | [15 empty] | PREVISIONAL MONITORING (planning future expenses) | [15 empty] | DONOR /FINANCIAL MONITORING - TO DATE |  |  |  | COMMENTS / QUALITATIVE INFORMATION (to be completed by the project manager during the reconciliation meeting with the administrative manager) | REGIONAL MANAGEMENT FEEDBACK (to be completed by regional coordinator in response to comments, questions, suggestions...) | PARTICIPANTS FEEDBACK
Project codeCode provided by administrative manager | Local activity codeCode provided by administrative manager | Budget line manager (Who?) | Budget lines (donor format or own funds - identical to budget formulation) | NB (Unit) | Freq (M) | Unit Cost - Project currency | Uni cost EUR (auto calculation) | Total Cost Project currency | Total Cost EUR (auto calculation) | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | TOT REALIZED (local currency) | TOTAL REALIZED EUROS | % completed to date | Balance at date | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | TOT ACTUAL + PLANNED local currency | TOTAL ACTUAL + FORECAST EUROS | Landing on overall budget | Balance on overall budget | Donor code 1 | Donor code 2 | Donor code 3 | Donor code 4
|  |  |  | 3 | 3 | 150 | 0 | 1350 | 0 | BUDGET MONITORING (actual project expenditure verified with administrative manager) M1: 450; BUDGET MONITORING (actual project expenditure verified with administrative manager) M2: 0; BUDGET MONITORING (actual project expenditure verified with administrative manager) M3: 150; BUDGET MONITORING (actual project expenditure verified with administrative manager) M4: 0; BUDGET MONITORING (actual project expenditure verified with administrative manager) M5: 0 | 600 | 0 | 44.44% | 750 | [11 empty] | 450 | 1050 | 0 | 77.78% | 300 | 375
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[7 empty] | 0 | 0 | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | [12 empty] | 0 | 0 | #DIV/0! | 0 | 0
[38 empty] | 0 | 0 | #DIV/0! | 0 | 0
[38 empty] | 0 | 0 | #DIV/0! | 0 | 0
[38 empty] | 0 | 0 | #DIV/0! | 0 | 0
[38 empty] | 0 | 0 | #DIV/0! | 0 | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
Note on H4: ====== ID#AAABicsSqCA (2025-04-24 09:01:05) =H*H1 -darnaudet valerie
Note on J4: ====== ID#AAABicsSqB8 (2025-04-24 09:01:05) =I*H1 -darnaudet valerie
Note on AP4: ====== ID#AAABicsSqCE (2025-04-24 09:01:05) =AO*H1 -darnaudet valerie
Note on AT4: ====== ID#AAABicsSqCQ (2025-04-24 09:01:05) =colonne Z * X% -darnaudet valerie